## Project_Register
source_record_id | project_id | field_name | source_value | unit | note
PR-001 | RW-14 | project_name | Oak Lane retaining wall and drainage closeout | text | local road improvement package
PR-002 | RW-14 | project_limits | STA 0+000 to STA 0+085 | text | retaining wall, perforated drain, and backfill
PR-003 | RW-14 | review_stage | civil closeout quantity check | text | artifact-only review package
PR-004 | RW-14 | coordinate_datum | Site grid RW14-2026 | text | matches survey record header
PR-005 | RW-14 | vertical_datum | Local benchmark BM-14A = 100.000 m | m | bench mark for wall-top and drain invert shots

## Pay_Item_Schedule
source_record_id | project_id | pay_item | description | scheduled_quantity | unit | station_start | station_end | note
PS-001 | RW-14 | RW-CONC | reinforced concrete retaining wall | 36.2 | m3 | 0+000 | 0+085 | schedule before field measure
PS-002 | RW-14 | RW-REBAR | reinforcement steel for retaining wall | 1830 | kg | 0+000 | 0+085 | pay item summary
PS-003 | RW-14 | DRAIN-AGG | free-draining aggregate behind wall | 19 | m3 | 0+000 | 0+085 | schedule before field measure
PS-004 | RW-14 | GEOTEXTILE | separation geotextile behind wall | 168 | m2 | 0+000 | 0+085 | schedule before field measure
PS-005 | RW-14 | WALL-EXC | retaining wall excavation | 92 | m3 | 0+000 | 0+085 | schedule before field measure
PS-006 | RW-14 | DRAIN-PIPE | 100 mm perforated collector drain | 76 | m | 0+000 | 0+085 | perforated pipe run
PS-007 | RW-14 | CONC-TEST | concrete compressive strength reports | 3 | each | 0+000 | 0+085 | one per wall pour
PS-008 | RW-14 | SURVEY-ASB | as-built elevation check points | 6 | each | 0+000 | 0+085 | wall top and drain invert checks

## Control_Points
source_record_id | project_id | point_id | northing | easting | elevation_m | description
CP-001 | RW-14 | BM-14A | 5000 | 1000 | 100 | temporary benchmark on hydrant flange
CP-002 | RW-14 | CTRL-14-1 | 5012.45 | 1044.28 | 100.842 | alignment control spike
CP-003 | RW-14 | CTRL-14-2 | 5048.91 | 1081.735 | 101.107 | north end control nail